## Slide 1
A bounded pilot for proposal decisions
Suggested six-week pilot with one team
Map approval decisions and incomplete commercial inputs before selecting broader automation.
Confirm the pilot objective, accountable reviewer and specialist capacity before any commitment.
Sample outputs · Suggested wording · Customer review pending
1
stratumgenops.com
Notes: This proposal starts with the operating issue. The note says approvals take too long, but it also identifies missing commercial inputs and unclear ownership. We propose a six-week pilot with one team to examine those decisions and handoffs. We have not established the cause of delay or a quantified benefit. The immediate decision is to confirm the objective, reviewer and necessary capacity.
Source: original pilot narrative, interactions 1–3. No real client or employer material.

## Slide 2
The source supports a bounded investigation
Source facts
Proposal approvals take too long.
Commercial inputs are incomplete.
Approval ownership is unclear.
Working hypothesis
Decisions and handoffs may constrain progress.
The source does not establish causation.
An AI writing tool may not address the issue.
Sample outputs · Suggested wording · Customer review pending
2
stratumgenops.com
Notes: Separate the supplied facts from the hypothesis. The note records incomplete inputs and unclear ownership. It does not measure how much delay each factor causes. The suggested response is to map the decisions and test a bounded workflow. Buying a writing tool remains an alternative to examine once the cause is better understood. Reviewer capacity and specialist coverage are still open.
Source: original pilot narrative, interactions 1–3. No real client or employer material.

## Slide 3
The suggested scope remains six weeks and one team
Wider rollout requires a separate scope decision
Prepare the decision map, source inventory and suggested recommendation for review.
Keep proposal material, presenter notes and commercial assumptions connected to that scope.
Agree acceptance criteria and responsibilities before treating this outline as contracted work.
Sample outputs · Suggested wording · Customer review pending
3
stratumgenops.com
Notes: The source boundary is six weeks and one team. The suggested work organizes the decision map, evidence and recommendation. It also prepares related materials for review. The suggested outputs and acceptance criteria require customer agreement. This is a scope-preparation example, not a complete or effective statement of work. No organization-wide rollout is included in the source.
Source: original pilot narrative, interactions 1–3. No real client or employer material.

## Slide 4
A shorter schedule needs an explicit delivery decision
Option | Consequence | Required decision
Equivalent redesign | Preserve outputs only with authorized replacement expertise and confirmed capacity. | Confirm who can do the work.
Phased entry | Start with bounded assessment. Keep the remaining intended result and later gates explicit. | Agree the sequence and remaining work.
Changed promise | Remove specialist-dependent outputs and state the narrower result. | Accept or reject the changed result.
Sample outputs · Suggested wording · Customer review pending
4
stratumgenops.com
Notes: The second conversation requests four weeks without specialist coverage and the same outputs. That request does not prove equivalent delivery. An alternative person needs the relevant judgment, authority and available capacity. Phasing may change the sequence while preserving the intended wider result. Reducing outputs changes the promise and requires a different decision. None of these options is automatically approved.
Source: original pilot narrative, interactions 1–3. No real client or employer material.

## Slide 5
The clarification preserves the current proposal
Retained
Six-week, one-team suggested scope.
Original source inventory.
Earlier decision history.
Review pending
The four-week option.
Specialist and reviewer capacity.
Commercial inputs and affected revisions.
Sample outputs · Suggested wording · Customer review pending
5
stratumgenops.com
Notes: The third interaction clarifies that four weeks is an option rather than an agreed replacement. A practice lead can review scope, but specialist capacity and commercial inputs remain unresolved. We retain the six-week proposal as the working reference. We preserve the earlier request and its status, rather than erasing it. The proposal, script and commercial assumptions require targeted review. The original source inventory remains valid.
Source: original pilot narrative, interactions 1–3. No real client or employer material.

## Slide 6
The next decision is the delivery boundary
Confirm the scope and capacity before release
Select the delivery option with its consequences visible.
Supply approved effort, rates and acceptance criteria.
Review each affected revision and authorize any external release separately.
Sample outputs · Suggested wording · Customer review pending
6
stratumgenops.com
Notes: The next decision is to select the delivery boundary and resolve capacity. The workbook requires approved effort and rate inputs before calculating an estimate. This example has no approved estimate, signed contract, live customer processing or measured commercial outcome. Review each affected revision and authorize release separately. The sample material demonstrates continuity and connected work, not completed delivery.
Source: original pilot narrative, interactions 1–3. No real client or employer material.